## Master Timeline
MASTER'S RESEARCH & ENGINEERING PROJECT TIMELINE (2026 - 2027)
Phase | Month | Week | Task Name | Track | Deliverable | Target Date | Status
Phase 1: Setup & EDA | October 2026 | Week 1 | Download IEEE-CIS Dataset & Setup Env | Data Science | Raw CSVs loaded, Jupyter EDA Notebook working | 2026-10-10 | In Progress
Phase 1: Setup & EDA | October 2026 | Week 2 | Dockerized Stack & Database Initialization | Software Eng | PostgreSQL & Redis running in Docker Compose | 2026-10-17 | Pending
Phase 1: Setup & EDA | October 2026 | Week 3 | Data Cleaning & Temporal 80/20 Train-Test Split | Data Science | clean_train.parquet & clean_test.parquet exported | 2026-10-24 | Pending
Phase 1: Setup & EDA | October 2026 | Week 4 | Formal Proposal Sign-off with Advisor | Academic | Approved 1-page Master's Proposal Document | 2026-10-31 | Pending
Phase 2: ML Engine | November 2026 | Week 5-6 | Train Tabular Baselines (XGBoost & LightGBM) | Data Science | Baseline PR-AUC & Recall@Top-1% results | 2026-11-14 | Pending
Phase 2: ML Engine | November 2026 | Week 7-8 | Build & Train Heterogeneous GraphSAGE | Data Science | PyG HeteroData trained with Focal Loss; beats baseline | 2026-11-28 | Pending
Phase 3: Web App | December 2026 | Week 9-10 | Export GNN to ONNX & Build Redis Subgraph Pipeline | Software Eng | FastAPI endpoint with sub-30ms scoring latency | 2026-12-12 | Pending
Phase 3: Web App | December 2026 | Week 11-12 | Build React Triage Dashboard & Live WebSocket Feed | Frontend / UI | Interactive D3/Force-graph canvas & live alert triage | 2026-12-26 | Pending
Phase 4: Journal Submission | January 2027 | Week 13-15 | Stress Testing & Paper Drafting (IEEE / ACM Format) | Academic | 8-10 page complete paper manuscript draft | 2027-01-23 | Pending
Phase 4: Journal Submission | February 2027 | Week 16-17 | SUBMIT RESEARCH PAPER TO TARGET JOURNAL | MILESTONE | Journal submission confirmation receipt | 2027-02-15 | CRITICAL
Phase 5: Thesis Writing | March 2027 | Week 18-21 | Author Thesis Chapters 1 to 3 (Intro, Lit Review, Arch) | Academic | First 40 pages of thesis draft submitted to advisor | 2027-03-31 | Pending
Phase 5: Thesis Writing | April 2027 | Week 22-25 | Author Thesis Chapters 4 to 6 (Experiments, Discussion) | Academic | Complete 70+ page thesis document compiled | 2027-04-30 | Pending
Phase 5: Thesis Writing | May 2027 | Week 26-29 | Advisor Review Revisions & Journal Feedback Incorporation | Academic | Revised pre-defense thesis manuscript | 2027-05-31 | Pending
Phase 6: Final Defense | June 2027 | Week 30-33 | Pre-Defense Submission & Presentation Slide Deck | Academic | Formal thesis submission & 25-slide defense deck | 2027-06-25 | Pending
Phase 6: Final Defense | July 2027 | Week 34-35 | ORAL MASTER'S THESIS DEFENSE | MILESTONE | Oral presentation, live software demo, final degree signoff | 2027-07-15 | CRITICAL

## Milestone Summary
Key Degree Milestones | Target Deadline | Deliverable Type
Proposal Sign-off | October 31, 2026 | Approved Proposal Document
Baseline ML Performance Verified | November 28, 2026 | PR-AUC Benchmark Table
System Architecture Prototype Ready | December 26, 2026 | Sub-30ms API + React Dashboard
Journal Paper Submission | February 15, 2027 | 8-10 Page Academic Manuscript
Full Thesis Book Draft | April 30, 2027 | Chapters 1-6 Master's Dissertation
Master's Oral Defense | July 15, 2027 | Oral Examination & Live System Demo